CULTURAL EXPLORER OF MALAYSIA

Complete Development Workflow Guide

Phang Sook May (22074090)  |  From UI complete → Full MVP

How to use this guide This document is your step-by-step development mentor from the point where your 5 HTML/CSS screens are done. Read it top to bottom once, then use each section as a reference when you reach that stage. Every command, convention, and workflow described here is tailored to your exact project setup: Vanilla JS, no bundler, GitHub repo at github.com/SookMayyy/cultural-explorer.

# 1.0  Where You Are Now — Quick Audit

Before writing a single new line of code, do this 10-minute audit. It stops you from building on a shaky foundation.

## 1.1  Checklist: confirm your foundation is solid

| # | Check | What to look for |
| --- | --- | --- |
| 1 | Open index.html in Chrome — does it load without errors? | Open DevTools (F12) → Console tab. Zero red errors = good. |
| 2 | Check every CSS file is linked | In index.html: count <link> tags. One per screen + global.css. |
| 3 | Resize browser window to 390px wide (but not mandatory) (currently need web page size consistently for all pages) | Go to DevTools → Toggle device toolbar (Ctrl+Shift+M) → set to 390×844. Do all 5 screens look correct at this size? |
| 4 | Check no broken image paths | DevTools → Console. "Failed to load resource" messages = broken path. |
| 5 | Verify scripts load in correct order | DevTools → Network tab → reload → filter by JS. Scripts must load in: data → utils → components → router → app |
| 6 | Confirm git repository is initialised | In PowerShell: git status. Should show your repo state, not an error. |

## 1.2  Your exact project state right now

You have: 5 HTML screens (home, map, stamps, quiz, profile) + their CSS files. You do NOT yet have: working navigation, JavaScript logic, data layer, persistence, or any mini-games. That is exactly the right place to be — UI first is the correct approach. Now you build the working app on top of the finished UI.

# 2.0  Frontend Development Workflow

## 2.1  The golden rule: build in vertical slices

A vertical slice means: one complete feature, working end-to-end, before moving to the next feature. This is the opposite of building all HTML first, then all JS, then all CSS separately.

| Approach | Result |
| --- | --- |
| ❌ Horizontal (wrong): build all HTML → all CSS → all JS | You have 5 dead screens for weeks. Hard to test. Easy to lose motivation. CSS breaks when JS is added. |
| ✓ Vertical (correct): build one complete screen at a time | You have something working and testable after each slice. Bugs caught early. Demo-able at any point. |

## 2.2  Screen implementation order — and why

This order is chosen carefully. Each screen unlocks the next — skip it and you will be blocked.

| Step | Screen | Why first? | Blocks what comes after |
| --- | --- | --- | --- |
| 1 | Navigation/Router | Everything else requires navigation to work. Without this, your screens are isolated dead-ends. | Every other screen |
| 2 | Home screen | Simplest — mascot greeting + two buttons. Perfect first test of router. | Login, map entry |
| 3 | Login screen | Required before any save/progress feature. Class PIN + Avatar path (no password). | Progress, stamps, all save features |
| 4 | Map screen | Core navigation hub. Click-to-state is the central game mechanic. | Narrative, mini-games, all state content |
| 5 | Narrative/Discovery cards | The main learning screen. Must work before any mini-game. | All mini-games, quiz, reward |
| 6 | Quiz screen (MCQ) | Simplest mini-game. Validates the quiz data layer. | Drag-match, guess, harder games |
| 7 | Reward screen | Stamp award animation. Requires Storage.awardStamp(). | Stamp book display |
| 8 | Stamp book | Reads earned stamps from storage. Requires reward to write them first. | Profile stats |
| 9 | Profile screen | Reads all stats. Works correctly only after everything above. | Settings, progress report |
| 10 | Mini-games (drag, guess, memory…) | Enhancements on top of a working core. Add one at a time. | Polish, animations |

## 2.3  How to structure reusable components

Your CLAUDE.md already defines the correct pattern: render() + init(). Here is how to apply it consistently.

The component pattern — always follow this Every reusable piece (topbar, navbar, mascot, quiz card, stamp item) is a JS object with exactly two methods: ComponentName.render(data) → returns an HTML string (no DOM access here) ComponentName.init(el, data) → attaches event listeners to the already-rendered DOM Why this split? Because innerHTML replaces the DOM, destroying event listeners. render() builds the string. Your page calls innerHTML. Then init() wires up events. → Never attach event listeners inside render() → Never do DOM queries inside render() → Always call init() AFTER the HTML has been injected

Example — Topbar component:

// js/components/topbar.js const Topbar = { render({ title, showBack = false, backTarget = "home" }) { return ` <div class="topbar"> ${showBack ? `<button class="topbar__back" data-back="${backTarget}">←</button>` : ""} <span class="topbar__title">${title}</span> <div class="topbar__pts" id="pts-display">⭐ ${Storage.getPoints()} pts</div> <button class="settings-btn" data-nav="settings">⚙️</button> </div>`; }, init(containerEl) { // Nothing needed — data-nav and data-back are wired by Router }, updatePoints() { const el = document.getElementById("pts-display"); if (el) el.textContent = "⭐ " + Storage.getPoints() + " pts"; } };

## 2.4  When to create a new JS file

| Situation | Decision |
| --- | --- |
| Code is used on more than one screen | → Put it in js/components/ as a component |
| Code is only used on one screen | → Put it in js/pages/screenName.js |
| Code is pure data (no DOM, no events) | → Put it in js/data/ (states.js, quizzes.js) |
| Code is a utility (shuffle, clamp, etc.) | → Put it in js/utils/helpers.js |
| Code reads/writes localStorage | → It all belongs in js/utils/storage.js ONLY |
| You have more than ~80 lines in one function | → Split it. Each function should do one thing. |

## 2.5  Asset organisation rules

| Asset type | Where it goes + naming rule |
| --- | --- |
| State flags | assets/images/flags/{stateId}.png e.g. penang.png, kedah.png |
| Mascot characters | assets/images/mascots/rimau.png, rimau-wave.png, wak.png, wak-wave.png |
| Stamp illustrations | assets/images/stamps/{stateId}.png e.g. penang-stamp.png |
| UI backgrounds | assets/images/ui/home-bg.png, profile-bg.png, batik-pattern.png |
| Photobooth frames | assets/images/photobooth/{stateId}-frame.png |
| Sound effects | assets/audio/sfx/stamp.mp3, correct.mp3, wrong.mp3, tap.mp3 |
| State music stings | assets/audio/music/penang-sting.mp3, kelantan-sting.mp3 |
| Mascot voice lines | assets/audio/mascot/rimau-penang-entry.mp3 |
| Prototype references | docs/prototype/home.png, map.png, quiz.png (exported from Figma) |

File naming rules — always follow these → All lowercase, words separated by hyphens: penang-stamp.png NOT PenangStamp.PNG → No spaces in any file or folder name: home background.png will BREAK your CSS url() → File extensions always lowercase: .png .mp3 .css .js — never .PNG .MP3 → State IDs must match exactly: if your data uses "ns" for Negeri Sembilan, the image must be ns.png

# 3.0  Feature Implementation Order

This is the exact order in which to build features. Do not skip ahead — each item creates the foundation for the next.

## Sprint 1 — The Navigation Skeleton  (target: 3–4 days)

Goal: be able to tap any button and reach any screen. Nothing else. No data, no logic, no styling changes.

| # | Feature | What to build |
| --- | --- | --- |
| 1a | Router | js/router.js — maps screen IDs to view objects. Reads data-nav attributes. Shows/hides .screen divs. |
| 1b | Basic app.js | js/app.js — calls Router.init() on DOMContentLoaded. That's it for now. |
| 1c | Wire all nav buttons | Add data-nav="map" to every navbar and CTA button. Test: can you reach every screen? |
| 1d | Back button | Topbar back arrow calls Router.back(). Uses sessionStorage to remember history. |
| 1e | Active navbar highlight | Router sets .active class on the correct nav item after each navigation. |

Definition of done — Sprint 1 ✓ Click Home → Map → Stamps → Quiz → Profile → Back. All work. ✓ The active tab in the navbar is highlighted correctly on each screen. ✓ No JavaScript errors in the console on any screen. ✓ Commit: "feat: add navigation router and wire all screens"

## Sprint 2 — Data Layer + Storage  (target: 2–3 days)

Goal: your game has a memory. It knows who the player is and what they have done.

| # | Feature | What to build |
| --- | --- | --- |
| 2a | Storage utility | js/utils/storage.js — getPoints(), addPoints(), getStamps(), awardStamp(), getPlayer(), setPlayer(), isCompleted(). All use localStorage with ce_ prefix. |
| 2b | States data file | js/data/states.js — STATES_DATA array for all 7 prototype states. Each has: id, name, region, mascot, color, flagFile, locked, unlockAfter. |
| 2c | Quiz data file | js/data/quizzes.js — QUIZ_QUESTIONS array. Min 4 questions per state. |
| 2d | Dialogue data file | js/data/dialogue.js — mascot dialogue strings for every state and phase. |
| 2e | helpers.js | shuffle(), getState(id), unlockedUpTo(completedIds), pct(current, total), wait(ms). |

Definition of done — Sprint 2 ✓ Open browser console: type Storage.getPoints() → returns 0 ✓ Type Storage.addPoints(10) → returns 10 ✓ Type STATES_DATA.length → returns 7 ✓ Reload the page — type Storage.getPoints() again → still 10 (persisted!) ✓ Commit: "feat: add data layer — states, quizzes, dialogue, storage utility"

## Sprint 3 — Login System  (target: 2 days)

Goal: student can log in (Class PIN + Avatar) and their display name appears throughout the app.

| # | Feature | What to build |
| --- | --- | --- |
| 3a | Login screen HTML/CSS | views/login.html — two paths: MOE ID (text input) and Class PIN + Avatar grid. |
| 3b | Login page JS | js/pages/loginPage.js — validates PIN format, handles avatar selection, writes to Storage.setPlayer(). |
| 3c | Guest mode | "Try without login" button — sets authType: "guest" in storage. Shows warning: "progress won't be saved." |
| 3d | Auth guard | If no player in Storage, redirect to login. Check on home screen init. |
| 3e | Display name in topbar | Topbar component reads Storage.getPlayer().displayName and shows it. |

## Sprint 4 — Map Screen Logic  (target: 3 days)

Goal: tap a state on the map or sidebar → mascot appears → popup shows → can enter the state.

| # | Feature | What to build |
| --- | --- | --- |
| 4a | Sidebar builder | js/pages/mapPage.js — reads STATES_DATA, calls withLockStatus(), renders sidebar list with correct explored/locked/not-explored status. |
| 4b | SVG map click handlers | Each <path> element gets an event listener. Locked states: show friendly "still locked" mascot message. Unlocked: call selectState(). |
| 4c | State popup | selectState() shows popup with flag, name, status, Explore button. Updates map highlight. |
| 4d | Mascot entry | MascotController.enter() + speak() with correct dialogue from getDialogue(stateId, phase). |
| 4e | Enter state | Popup "Explore" button sets sessionStorage.activeState = stateId and navigates to narrative screen. |
| 4f | Progress badge | "X of Y explored · Z%" badge updates from Storage.completedCount() and STATES_DATA.length. |

## Sprint 5 — Narrative / Discovery Cards  (target: 3 days)

Goal: student sees cultural content cards with mascot narration for the selected state.

| # | Feature | What to build |
| --- | --- | --- |
| 5a | Card renderer | narrativePage.js — reads sessionStorage.activeState, loads state from STATES_DATA, renders 4 swipeable cards (food, landmark, tradition, dialect). |
| 5b | Card swipe | CSS scroll-snap on horizontal container. Arrow buttons for desktop. Touch swipe events for mobile. |
| 5c | Mascot per card | Each card triggers mascot.speak() with the card-specific dialogue line. |
| 5d | Tap-to-reveal fun fact | Each card has a hidden "Did you know?" element. Tapping the card flips it open with a CSS transition. |
| 5e | Proceed to mini-game | After last card, "I'm ready!" button appears. Routes to the mini-game for this state. |
| 5f | Mark state as visited | narrativePage.init() calls Storage.markVisited(stateId) immediately on entry. |

## Sprint 6 — Quiz System  (target: 2–3 days)

Goal: complete end-to-end quiz — question shown, answer selected, feedback given, score saved.

| # | Feature | What to build |
| --- | --- | --- |
| 6a | QuizWidget component | js/components/quizWidget.js — render(question, options) and init(el, correctIndex, onResult). Handles correct/wrong states, retry, explanation text. |
| 6b | Quiz page controller | js/pages/quizPage.js — loads 4 questions for current state, cycles through them, tracks score. |
| 6c | Adaptive difficulty | Track consecutive correct answers. After 2 correct: serve a "hard" tagged question next. Wrong: serve "easy" again. |
| 6d | Quiz completion | After 4 questions: calculate score, call Storage.saveScore(stateId, score), navigate to reward screen with score in sessionStorage. |
| 6e | Mascot feedback | correct → mascot.celebrate(). Wrong → mascot.think() + hint restatement of the cultural fact. |

## Sprint 7 — Reward + Stamp System  (target: 2 days)

Goal: stamp flies in, is permanently saved, stamp book shows it correctly.

| # | Feature | What to build |
| --- | --- | --- |
| 7a | Reward screen | js/pages/rewardPage.js — reads sessionStorage.quizScore, displays mascot celebration, triggers stamp animation. |
| 7b | Stamp fly-in animation | CSS @keyframes stamp-land: drops from above, slight rotation, bounce on land. Play stamp.mp3. |
| 7c | Storage writes | Storage.awardStamp(stateId), Storage.markCompleted(stateId), Storage.addPoints(score * 5). |
| 7d | Stamp book display | stampsPage.js — reads Storage.getStamps(), renders earned stamps with gold border + ✓, unearned as dashed ? circles. |
| 7e | Tap earned stamp | Tapping an earned stamp opens a small summary card for that state (key fact + mascot emoji). |

## Sprint 8 — Extra Mini-Games  (one per sprint after core is done)

| Mini-game | What to build + data needed |
| --- | --- |
| Drag & Match | DragMatch component — shuffle food chips, tap chip + tap drop zone. Data: dragPairs[] in STATES_DATA per state. |
| Guess the State | GuessPage.js — 4 progressive clues shown one by one. Scoring: clue 1 correct = 20pts, clue 4 correct = 5pts. Data: GUESS_ROUNDS. |
| Word Scramble | Shuffle letters of a dialect word into buttons. Tap in correct order. Show/hide progress as letters placed. |
| True/False Swipe | Swipe card right (True) or left (False). CSS transform on drag. 5 statements per state. |
| Memory Card Flip | 4×3 grid. CSS flip animation. Match food image ↔ food name. Track attempts and time. |
| Photobooth | HTML Canvas. Draw avatar + mascot + selected decorative frame. toBlob() → download PNG link. |

# 4.0  Debugging & Testing Process

## 4.1  DevTools — the most important tool you have

Press F12 in Chrome/Edge to open DevTools. Learn these 4 panels — they solve 95% of all problems.

| Panel | What it solves + how to use it |
| --- | --- |
| Console | JavaScript errors, console.log output. RED = error. Expand it — it shows file + line number. Click the link → goes straight to the bug. |
| Elements | HTML + CSS inspection. Right-click any element → Inspect. See its computed styles. Double-click to edit live. Use to diagnose layout problems. |
| Network | See every file request. Filter by JS or CSS. Red rows = 404 (wrong file path). Check this when assets or scripts don't load. |
| Application | Under Storage → Local Storage → localhost:3000 — see every value your game saves. Edit or delete values here to test edge cases (e.g. test stamp book with 0 stamps). |

## 4.2  Debugging HTML/CSS layout issues

5-step CSS debug process 1. Open DevTools → Elements panel. Click the element that looks wrong. 2. Look at the right-side Styles panel. Is the rule there? Is it crossed out (overridden by something more specific)? 3. Add outline: 2px solid red to the element in DevTools (temporary). See its actual size and position. 4. Check the Box Model (below Styles). Are margins, padding, border values unexpected? 5. Work up the DOM tree — the bug is often in a parent element (e.g. overflow: hidden cutting off a child).

Common CSS bugs and their fixes:

| Symptom | Likely cause + fix |
| --- | --- |
| Element overflows off the right edge | Parent has no width set, or child uses position: absolute without positioned parent. Add overflow: hidden to parent temporarily to diagnose. |
| Flexbox items not centering | Forgot align-items: center OR justify-content: center on the PARENT, not the children. |
| Absolute element appears in wrong place | The positioned ancestor is not position: relative. Add position: relative to the correct parent. |
| CSS not applying at all | Class name typo, or CSS file not linked, or specificity conflict. Check in DevTools Styles — is the rule greyed out? |
| Animation runs once then stops | Missing animation-fill-mode: forwards OR animation is on wrong element. |
| Mobile layout looks different from desktop | Width is using px instead of % or vw, or missing viewport meta tag in HTML head. |

## 4.3  Debugging JavaScript errors

How to read a JS error in the console Uncaught TypeError: Cannot read properties of undefined (reading "id") at mapPage.js:42 → Line 1: what went wrong (tried to read .id on something that is undefined) → Line 2: exactly which file and line number → Click "mapPage.js:42" — DevTools jumps to that exact line → Look at the variable mentioned. Add console.log(thatVariable) one line above → what is it? → Trace back: where was it supposed to get a value? Was the function called before data loaded?

Common JS bugs in this project:

| Error message | What it means + fix |
| --- | --- |
| Cannot read properties of null (reading "addEventListener") | document.querySelector() returned null — the element does not exist yet when the script runs. Solution: move your JS to run after DOMContentLoaded. |
| ReferenceError: Storage is not defined | Storage (or any global) was not loaded yet. Check script load order in index.html — data → utils → components → router → app. |
| SyntaxError: Unexpected token | Typo in JS — missing bracket, comma, or quote. The line number in the error is where JS gave up, not always where the typo is. Look 1–3 lines above. |
| Screen shows nothing after navigate | view.render() returned empty string, OR innerHTML was set but init() not called, OR CSS has the wrong class for showing active screens. |

## 4.4  Testing process — do this after every feature

| # | Test type | How to do it |
| --- | --- | --- |
| 1 | Happy path test | Use the feature exactly as a student would. Does it work correctly? |
| 2 | Edge case test | What if the student taps really fast? What if they skip a step? What if localStorage is empty (first visit)? |
| 3 | Mobile test | DevTools → device toolbar → iPhone 12 Pro (390×844). Check at this size after every CSS change. |
| 4 | Console check | After every test: is the console clean? Zero errors allowed before committing. |
| 5 | Network check | DevTools Network tab: are any files returning 404? Fix broken paths before committing. |
| 6 | LocalStorage check | DevTools Application → Local Storage. Does saving/loading work? Clear storage and test a fresh start. |

Clean code habit: no console.log in committed code Use console.log freely while debugging. But before every commit, search your files for console.log and remove them. In VS Code / Cursor: Ctrl+Shift+F → search "console.log" across all files → remove before commit. Exception: you may keep console.error() for genuine error handling (e.g. failed fetch).

# 5.0  Git & GitHub Workflow

This section teaches you Git from zero in the context of your Cultural Explorer project. Every command is explained.

## 5.1  Understanding Git in plain language

Git is like a save system with unlimited undo. Every "commit" is a save point you can go back to. GitHub is the cloud storage where your save points live. A "branch" is a parallel universe — you make experimental changes there without touching your working code.

## 5.2  Daily workflow — the 6-step loop

Every working day follows this exact loop. Memorise it.

# 1. Start your day — make sure you have the latest code from GitHub git pull origin master # 2. Create a branch for the feature you are about to build git checkout -b feat/map-state-selection # 3. Build the feature. Test it. Make sure it works. # 4. Stage your changes (tell Git which files to save) git add . # adds ALL changed files git add js/pages/mapPage.js # OR add specific files only # 5. Commit (create the save point) git commit -m "feat(map): add state selection and mascot popup" # 6. Push your branch to GitHub git push origin feat/map-state-selection

## 5.3  What every Git command actually does

| Command | What it does in plain language |
| --- | --- |
| git status | Shows which files have changed since your last commit. Run this before staging to see what you are about to commit. |
| git pull origin master | Downloads the latest version of the master branch from GitHub and merges it into your current branch. Always do this at the start of each session. |
| git checkout -b feat/name | Creates a new branch called feat/name AND switches to it. You are now working in your own parallel version of the code. |
| git checkout master | Switches back to the master branch (your stable, working code). |
| git add . | Stages ALL changed files for the next commit. The . means "everything in this folder and below." |
| git add filename.js | Stages ONE specific file. Use when you only want to commit some of your changes. |
| git commit -m "message" | Creates a save point with all staged changes + the message you wrote. This is permanent and traceable. |
| git push origin branch-name | Uploads your local commits to GitHub on the specified branch. Others can now see your work. |
| git log --oneline | Shows a compact list of all commits with their short IDs and messages. Use to review your history. |
| git diff | Shows exactly what changed in every file since the last commit — line by line. Very useful before committing. |
| git stash | Temporarily saves your uncommitted changes so you can switch branches. Use when you need to context-switch quickly. |
| git stash pop | Restores the changes you stashed. Run this when you come back to the feature. |

## 5.4  Branch naming convention

Use a consistent prefix so branches are easy to identify in GitHub. Your CLAUDE.md already defines this:

| Branch prefix | When to use it |
| --- | --- |
| feat/description | New feature: feat/map-state-selection, feat/quiz-mcq, feat/stamp-book-display |
| fix/description | Bug fix: fix/navbar-active-state, fix/stamp-animation-not-triggering |
| ui/description | Visual/CSS changes: ui/home-background-image, ui/quiz-card-polish |
| refactor/description | Code cleanup without changing behaviour: refactor/extract-mascot-component |
| content/description | Adding data only: content/kedah-dialogue, content/quiz-questions-melaka |
| docs/description | Documentation only: docs/update-claude-md |

## 5.5  Commit message format

Your project uses the Conventional Commits standard. This format makes your commit history readable like a changelog.

Format: type(scope): short description type: feat ¦ fix ¦ ui ¦ refactor ¦ content ¦ docs ¦ test scope: the screen or component affected (optional but helpful) description: present tense, lowercase, no period at end Good examples: feat(map): add clickable SVG state paths with mascot popup fix(quiz): correct answer not highlighting after wrong attempt ui(home): replace placeholder SVG with illustrated background image content(penang): add all 4 cultural content cards and dialogue refactor(mascot): extract TypewriterBubble into its own component docs: update CLAUDE.md with sprint 3 progress Bad examples (avoid these): "changes" ← too vague "fixed stuff" ← meaningless "WIP" ← never commit broken code as WIP "update map.html" ← says what file, not what changed

## 5.6  When to commit — the rule

Commit rule: one feature, one commit — green tests only Commit when: you just finished one complete, testable thing and the app still runs. ✓ Good commit points: — Navigation between all screens works — State selection + popup appears correctly — Quiz completes and saves score — Stamp animation plays correctly ✗ Never commit when: — There are red errors in the console — The feature is half-built — You are mid-refactor → If you want to save mid-work: use git stash (saves without committing) or commit with [WIP] prefix on a personal branch, then squash before merging.

## 5.7  Pull Request workflow

A Pull Request (PR) is how you safely merge a feature branch into master. Even as a solo developer, use PRs — they give you a review moment and a clean merge history.

# Step 1: Push your feature branch to GitHub git push origin feat/map-state-selection # Step 2: Go to github.com/SookMayyy/cultural-explorer # GitHub will show a banner: "feat/map-state-selection had recent pushes" # Click "Compare & pull request" # Step 3: Fill in the PR form: # Title: feat(map): add state selection and mascot popup # Description: what you built, what was tested, any known issues # Step 4: Merge (you are solo, so you are your own reviewer) # Click "Merge pull request" → "Confirm merge" # Step 5: Delete the feature branch (keep master clean) # GitHub shows "Delete branch" button after merge — click it # Step 6: Pull the merged code back to your local master git checkout master git pull origin master # Step 7: Create your next feature branch git checkout -b feat/narrative-cards

## 5.8  Avoiding merge conflicts

Merge conflicts happen when two versions of the same line of code differ. As a solo developer they are rare, but here is how to prevent and resolve them:

| Prevention rule | Why it helps |
| --- | --- |
| Always git pull origin master before starting a new branch | Ensures your branch starts from the latest code, not an old version. |
| Keep branches short-lived (1–3 days max) | Longer branches diverge more from master. Merge frequently. |
| One branch per feature | Never work on two unrelated features in one branch. |
| Never edit the same file in two branches simultaneously | If two branches both modify map.css, you will get a conflict. |

If a conflict does occur:

# Git marks conflicts in the file like this: <<<<<<< HEAD .map-title { color: purple; } ← your version ======= .map-title { color: blue; } ← incoming version >>>>>>> feat/map-state-selection # Fix: manually edit the file to keep the version you want. # Delete the <<<, ===, >>> markers. # Then: git add css/map.css git commit -m "fix: resolve merge conflict in map.css"

# 6.0  Recommended Development Process

## 6.1  Weekly focus guide

| Week | Focus area | Deliverable by end of week |
| --- | --- | --- |
| Week 1 | Navigation + Data layer | All screens reachable. Storage works. Data files seeded. |
| Week 2 | Login + Map logic | Student can log in. Tapping a state shows mascot + popup. |
| Week 3 | Narrative cards + Quiz | Cultural cards swipeable with mascot narration. MCQ quiz complete with score. |
| Week 4 | Reward + Stamp book | Stamp awarded on completion. Stamp book shows earned/unearned correctly. |
| Week 5 | Extra mini-games (2–3) | Drag & match + Guess the state + one more mini-game working. |
| Week 6 | Profile + Settings + Audio | Profile stats live. Sound effects working. Mute toggle. |
| Week 7 | Polish + Animations | Mascot animation fully working. Transition animations. Responsive check. |
| Week 8 | UAT Prep + Bug fixing | 5–8 participants tested. Critical bugs fixed. No console errors. |

## 6.2  MVP vs postpone — be ruthless

| Feature | Priority | Reasoning |
| --- | --- | --- |
| Navigation between all screens | MVP | Nothing works without this |
| Map: clickable states + popup | MVP | Core game mechanic |
| Narrative cards (4 types) | MVP | Main learning content delivery |
| MCQ Quiz + adaptive difficulty | MVP | Core assessment |
| Stamp award + stamp book display | MVP | Core reward system |
| Login: Class PIN + Avatar | MVP | Required for save progress |
| Mascot typewriter dialogue | High value | Differentiates from basic apps |
| Drag & match mini-game | High value | Required by FYP scope |
| Guess the state mini-game | High value | Required by FYP scope |
| Sound effects (sfx only) | Medium | Nice to have, easy to add |
| Background music | Postpone | Add last — complex + controversial in class |
| Photobooth | Postpone | Great extra feature, not core |
| Word scramble / memory game | Postpone | Add if time allows after MVP |
| Progress chart in profile | Postpone | Nice data visualisation, not required |

## 6.3  When to refactor code

The refactor trigger — three signs you need to clean up 1. Copy-paste: if you copied the same block of code into 2+ files → extract it into a component. 2. Function length: if a function is longer than ~40 lines → it is doing too many things. Split it. 3. Understanding delay: if you look at code you wrote 2 weeks ago and cannot understand it in 60 seconds → add comments or rename variables. → Refactor after each feature is stable, never mid-feature. → Create a branch: refactor/extract-quiz-widget, test it, then merge. → Never refactor and add features in the same commit.

## 6.4  How real frontend developers iterate

The professional workflow is not "design everything, then build everything." It is rapid cycles of: build → look at it → feels wrong → adjust → repeat. Here is what that looks like concretely:

- Build the screen in HTML/CSS — static, no JS. Open it in the browser at 390px. Does it feel right?

- If spacing or typography feels wrong: fix it before adding any JS. CSS bugs are much harder to find once event listeners are involved.

- Add the minimum JS to make it interactive. Test immediately. Fix what breaks.

- Step away for 20 minutes. Come back and look at it with fresh eyes. Does it feel like the prototype?

- Add a subtle animation or transition. Does it feel smoother? Keep it. Does it feel distracting? Remove it.

- Test on mobile. Something always breaks. Fix it.

- Commit. Move to the next feature.

# 7.0  Testing Milestones

These are your checkpoint moments — each milestone is a demo-able, stable version of the game.

| Milestone | Target week | Definition of done |
| --- | --- | --- |
| M1: UI Prototype Complete | Done ✓ | All 5 screens match Figma. No broken layouts at 390px. Zero console errors. |
| M2: Navigation Functional | Week 1 | All buttons navigate correctly. Back button works. Active nav tab highlights. |
| M3: Data Layer Working | Week 1 | STATES_DATA, Storage, Helpers all loaded. Test via console: no errors. |
| M4: First Playable Demo | Week 2–3 | Can log in → select Penang → see narrative cards → complete quiz → earn stamp. |
| M5: Core Mini-Games Working | Week 4 | Drag & match + Guess the state both complete correctly and award points. |
| M6: Save Progress Working | Week 4 | Close browser → reopen → stamps still there, points correct, visited states remembered. |
| M7: Full MVP Ready | Week 5–6 | All 7 prototype states playable end-to-end. All mini-games working. No blocker bugs. |
| M8: UAT Ready | Week 7 | App works on a real phone. Child-friendly SUS questionnaire prepared. Ethics form ready. |
| M9: Final Polish Phase | Week 8 | All animations smooth. Audio working with mute option. All known bugs fixed. Zero console errors. |

# 8.0  Quick Reference Cheat Sheet

## 8.1  The 5 questions to ask yourself before writing any code

- Which screen or feature is this for?

- Does this code belong in core/, components/, data/, pages/, or utils/?

- Does anything like this already exist that I can reuse?

- Will this work when localStorage is empty (first-time user)?

- Will this still look correct at 390px wide on a phone?

## 8.2  Commands you will use every single day

npm run dev # start the development server git status # see what has changed git pull origin master # get latest code git checkout -b feat/feature-name # start a new feature git add . # stage all changes git commit -m "feat(scope): description" # save your work git push origin feat/feature-name # upload to GitHub git checkout master # go back to stable code git log --oneline # review commit history

## 8.3  File you update most often

| File | Why you touch it |
| --- | --- |
| CLAUDE.md | Update sprint progress, change active task, add new constraints or decisions. |
| js/data/states.js | Add content for new states, update cultural data, fix information errors. |
| js/data/dialogue.js | Add mascot dialogue for new states or new phases. |
| css/global.css | Update design tokens (colours, spacing) when Figma spec changes. |
| index.html | Add new <script> tags when you create new JS files (in load order). |

Cultural Explorer of Malaysia  |  Development Workflow Guide  |  Phang Sook May (22074090)  |  Sunway University